## Project-GANTT
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 18 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | % | 36 project months from 15.10.2015 until 14.10.2018
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | 15.10.15 |  | Dec. |  | Feb. |  | Apr. |  | Jun |  | Aug. |  | Oct 16 |  | Dec. |  | Feb. |  | Apr. |  | Jun |  | Aug. |  | Oct 17 |  | Dec. |  | Feb. |  | Apr. |  | Jun. |  | Aug. | 14.10.18 project end |  |  |  |  | references
according workplan, LFM, proposal | [5 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | what and where are the results?
1 | Analysis on rural development and skills demand | Preparation | P3 CULS
1,1 | Local working groups established | event
action | establishment of the local working groups |  | P6-11, 17-28 | 1 | 4 | 4 | 2 | 100%
1,2 | Situation analyses on rural development and job demands | report
action | description of framework conditions in the regions |  | P6-11, P1, P3, P5 | 1 | 4 | 4 | 2 | 100%
action | Summary on job skills demand |  | P6-11 | 2 | 6 | 4 | 5 | 100%
action | collection and analysis of existing study programme examples |  | P6-11, P12-16 | 2 | 6 | 4 | 10 | 100%
action | Presentation of results on labour market and job deman analysis on the Kick-off meeting |  | P6-11 | 7 | 1 | 7 | 1 | 100%
action | short summary report on WP1 |  | P3 | 18 | 1 | 18 | 1 | 90%
2 | Establishment of new study programme and courses | Development | P6 Omsk
2.1 | Outline and study requirements defined | report
action | Clarification of professional studies requirements and elaboration of proposals for study programme outline |  | P6-11 | 2 | 4 | 2 | 6 | 100%
task | Detailed information about compulsory modules and entry exams for each of the aggregative group or majors. For RU: Agriculture, Economics, Management For KZ: Economics, Management |  | P6, Kazydub P11, Meleshenko | 3 | 2 | 3 | 2 | 100%
action | Clarification of possibility to open master programme with 90 ECTS in Russia and in Kazakhstan |  | P6 | 4 | 2 | 4 | 15 | 60%
action | Proposals of partner HEIs on outline of study programme |  | P6-11 | 4 | 2 | 4 | 6 | 100%
2.2 | Study programme elaborated | methodology
action | Proposals for final outline and content of the master programme on the kick-Off Meeting |  | P5, P6-11 | 7 | 1 | 7 | 1 | 100%
action | Definition of common general structure and content of study programme on the Kick-Off Meeting |  | P6-11 | 7 | 1 | 7 | 1 | 100%
action | Elaboration of study structure and draft syllabi of professional master |  | P6-11 | 5 | 6 | 6 | 14 | 95%
action | optional use of new courses in further education faculties |  | P6-11 | 5 | 12 | 7 | 13 | 95%
2.3 | Courses and modules are developed | service/ product
action | collection and research of existing module materials |  | P5-11 | 5 | 16 | 5 | 16 | 90%
action | development of new modules contents and detailed description |  | P6-11 | 10 | 14 | 10 | 14 | 65%
2.4 | Study programmes accredited, courses implemented | service/ product
action | developed study programmes are approved and recognised |  | P6-11 | 12 | 13 | 18 | 10 | 10%
action | course implementation and module conduction |  | P6-11 | 23 | 14
2,5 | Meetings | report
action | First coordination meeting in Omsk, P6 |  | P6-P8, P1 | 5 | 1 | 5 | 1 | 100%
action | First coordination meeting in Astana, P9 |  | P9-P11, P1 | 6 | 1 | 5 | 1 | 100%
action | Second coordination meeting in DAZ, P28 |  | P9-P11, P1 | 9 | 1 | 9 | 1 | 100%
action | Second coordination meeting in Ulan-Ude, P8 |  | P6-P8, P1 | 9 | 1 | 10 | 1 | 100%
action | Third joint regional coordination meeting in Michurinsk, P7 |  | P6-P11, P1-P5? | 20 | 1 | 20 | 1
3 | Capacity building of partner universities | Development | P2 WULS
3,1 | Equipment and literature purchased, equipment installed | teaching material
action | specification of equipment items and purchase |  | P6-11 | 5 | 21 | 12 | 14 | 20%
action | literature lists and purchase |  | P6-11 | 5 | 30 | 16 | 20 | 10%
3,2 | staff training and study trips to programme countries conducted | training material
action | Elaboration of requirements for the study trips |  |  | 4 | 4 | 7 | 5 | 100%
action | 1st study trip to P2,3 + didactic seminar P29 |  | P6-11 | 9 | 1 | 13 | 1 | 100%
action | 1st study trip selection of participants |  | P6-11 | 9 | 1 | 9 | 3 | 100%
action | 2nd study trip to P1,4 + didactic seminar P29 |  | P6-11 | 13 | 1 | 18 | 1 | 0%
action | 2nd study trip selection of participants |  | P6-11 | 13 | 1 | 14 | 4 | 100%
3,3 | Input/ backstopping visits from partner countries | event
action | visit and input of HEI partners in partner countries HEIs |  |  | 10 | 21 | 14 | 15 | 15%
4 | Practise orientation and stakeholder involvement | Development | P4 HfWU
4.1 | Practical training elements defined and developed | report
action | specification of practical skills to be developed during studies |  | P6-11 | 3 | 9 | 5 | 15 | 75%
action | development of practical trainings and teaching formats |  | P6-11 | 7 | 17 | 7 | 17 | 75%
4.2 | Stakeholder involvement institutionalised | service/ product
action | local working groups regular consultations (~2/ month) |  | P6-11 | 3 | 34 | 4 | 33 | 47%
action | implementation of internship schemes and/or project work with practise partners |  | P6-11 | 6 | 31 | 6 | 31 | 45%
5 | Sustainable agriculture and rural development platforms | Development | P5 RSAU
5.1 | Knowledge platform (+web) designed and accessible | service/ product
action | Elaboration of the ideals for knowledge platform |  | P5, P9 | 4 | 4 | 4 | 17 | 90%
action | concept development of the national network platforms |  |  | 3 | 12 | 5 | 15 | 95%
action | elaboration of the services (web contents, information, links) |  |  | 12 | 20 | 14 | 20 | 25%
action | sustainability and maintenance of network platform |  |  | 30 | 7
5.2 | Network Conferences are conducted | event
action | 1st project conference during project start phase |  | all | 7 | 1 | 7 | 1 | 100%
action | 2nd project conference interim |  | all | 19 | 1 | 22 | 1
action | 3rd project conference final phase |  | all | 31 | 1
6 | Study information and results dissemination | Dissemination | P9 KATU
6.1 | Project website, partner websites, links created and maintained | service/ product
action | project website preparation and launch EN & RU |  |  | 2 | 5 | 2 | 5 | 100%
action | project website maintenance and updates/ links with partner homepages |  |  | 5 | 32 | 5 | 32 | 45%
action | dissemination plan |  |  | 1 | 37 | 1 | 37 | 50%
action | dissemination & sustainability concepts |  |  | 13 | 3 | 11 | 9 | 90%
action | project poster EN & RU |  |  | 5 | 4 | 5 | 4 | 100%
action | project flyer |  |  | 8 | 4 | 8 | 8 | 100%
6,2 | Study programme and project results information | service/ product
action | elaboration of information material on study programmes |  |  | 12 | 13 | 18 | 7 | 10%
action | information events and dissemination of materials |  |  | 19 | 18
7 | Quality control and monitoring | Quality Plan | P1/P5
7.1 | M&E tools for project progress elaborated and iplemented | report | P1 UHOH
action | defining roles and procedures for project monitoring |  |  | 1 | 6 | 4 | 6 | 100%
action | Monitoring and reporting procedures of project progress established and communicated to project partners |  |  | 4 | 6 | 4 | 6 | 100%
action | monitoring and reporting of project progress |  |  | 4 | 33 | 4 | 33 | 47%
7.2 | Quality control of study plans and modules | report | P5 RSAU
action | definition of quality criteria for the study programme |  |  | 6 | 17 | 6 | 17 | 80%
action | presentation of quality criteria for the study programme at Kick-off |  |  | 7 | 1 | 7 | 1 | 100%
action | elaboration of the quality control plan |  |  | 14 | 2 | 14 | 7 | 80%
action | assessment of developed study plans and module performance |  |  | 23 | 14
8 | Project is successfully managed | Management | P1 UHOH
8.1 | Project steering committee meetings conducted | report
| 1SCM November 2015, Hohenheim |  |  | 2 | 0.4 | 2 | 0.4 | 100%
| 2SCM April 2016, Omsk (together with 1 project conference) |  |  | 7 | 1 | 7 | 1 | 100%
| 3SCM October 2016, Warsaw |  |  | 13 | 1 | 13 | 1 | 100%
| 4SCM July 2017, Astana (together with interim conference) |  |  | 19 | 1 | 22 | 1
| 5SCM January 2018, ? |  |  | 28 | 1
| 6SCM September 2018, Moscow (plus final conference) |  |  | 35 | 1
8.2 | Day to day management installed and in place | methodology
| project management tools installed |  |  | 1 | 6 | 1 | 6 | 100%
| regular aministrative, reporting and communication tasks |  |  | 1 | 36 | 1 | 36 | 50%
8,3 | Coordination of agreement tasks
| participation in EACEA project management seminar |  |  | 5 | 1 | 4 | 1 | 100%
| implementation and coordination of agreement tasks |  |  | 1 | 36 | 4 | 33 | 48%
| List of project partners with updated contact information send around, availale in intranet and regularly updated if needed |  | P1 | 4 | 1 | 4 | 1 | 100%
| Elaboration and signing of Partnership Agreement |  | P1, all partners | 4 | 4 | 6 | 9 | 100%

## partner
| Name des Partners (max. 60 Zeichen) |  | Town | Role | SCM | WP leads | national coordination | regional coordination | local coordination | study programme implementation | local work group members | module input and feedback | EU study trip organisation | didactic seminar organisation | PIC | Validation status | proposal contact/ communication
P1 | University of Hohenheim | UHOH | Stuttgart | Coodinator | x | 7, 8 | [5 empty] | x | study tour 1 | x | 999901900 | validated | martin.dieterich@uni-hohenheim.de; jochem.gieraths@uni-hohenheim.de
P2 | Warsaw University of Life Sciences | WULS-SGGW | Warsaw | partner | x | 3 | [5 empty] | x | study tour 2 |  | 999865137 | validated | aschwerk@yahoo.de; dymitryszyn@wp.pl
P3 | CZECH UNIVERSITY OF LIFE SCIENCES PRAGUE | CULS-CZE | Prague | partner | x | 1 | [5 empty] | x | study tour 2 |  | 999912570 | validated | lostak@pef.czu.cz
P4 | Hochschule für Wirtschaft und Umwelt Nürtingen-Geislingen | HfWU | Nürtingen | partner | x | 4 | [5 empty] | x | study tour 1 | x | 945895404 | validated | Heinrich.Schuele@hfwu.de
P5 | Russian State Agrarian University - Moscow Timiryazev Agricultural Academy | RSAU-MTAA | Moscow | partner | x | 5, 7 | RF |  |  |  |  | x |  |  | 986315013 | validated | a.merzlov@gmail.com; malk_msau@rambler.ru; valery.chumakov@yahoo.ca
P6 | Omsk State Agrarian University named after P.A. Stolypin | OSAU | Omsk | partner | x | 2 |  | x | x | X | WG1 |  |  |  | 951333321 | validated | Nat_staur@mail.ru, ng-kazydub@yandex.ru
P7 | Michurinsk State Agrarian University | MichSAU | Michurinsk | partner |  |  |  |  | x | x | WG2 |  |  |  | 969046685 | validated | yashina@mgau.ru
P8 | Buryat State Academy of Agriculture | BSAA | Ulan Ude | partner |  |  |  |  | x | x | WG3 |  |  |  | 934728376 | validated | zyampilova@list.ru
P9 | S.Seifullin Kazakh Agro Technical University | KATU | Astana | partner | x | 6 | KAZ | x | x | X | WG4 |  |  |  | 937165889 | validated | saraorazbek@mail.ru, nmeleshenko@mail.ru
P10 | A.Baitursynov Kostanay State University | KSU | Kostanay | partner |  |  |  |  | x | x | WG5 |  |  |  | 942793247 | validated | yelenakandalina@yahoo.com
P11 | Sh.Ualikhanov Kokshetau State University | KokSU | Kokshetau | partner |  |  |  |  | x | x | WG6 |  |  |  | 948627603 | validated | anuarka@mail.ru
P12 | Novosibirsk State Agrarian University | NSAU | Novosibirsk | partner | [7 empty] | x |  |  | 933756727 | validated | lyubov-83@bk.ru, dr.schindelov@ngs.ru
P13 | Samara State Agricultural Academy | SSAA | Samara | partner | [7 empty] | x |  |  | 934149383 | validated | interoffice.ssaa@mail.ru
P14 | Tambov State University named after G.R. Derzhavin | TSU | Tambov | partner | [7 empty] | x |  |  | 933335747 | validated | kolodina.m@yandex.ru, EmelyanovAV@yandex.ru
P15 | Yaroslavl State Agricultural Academy | YSAA | Yaroslavl | partner | [7 empty] | x |  |  | 933402968 | declared | shhukin@mail.ru
P16 | Stavropol State Agrarian University | SSAU | Stavropol | partner | [7 empty] | x |  |  | 958502494 | validated | serikovss@mail.ru, stavropolfad@yandex.ru
P17 | Ministry of Agriculture and Food of Omsk Region | MAFOR | Omsk | associate partner | [6 empty] | WG1 |  |  |  | 933099358 | declared | imanishe@mail.ru
P18 | Non-commercial partnership "Ecological Commitee" | NPEC | Omsk | partner | [6 empty] | WG1 |  |  |  | 998385596 | validated | Sergey.kostarev@gmail.com
P19 | Tambov Region Administration of Agriculture | TRAA | Michurinsk | associate partner | [6 empty] | WG2 |  |  |  | 932984995 | declared | mgv@agro.tambov.gov.ru
P20 | The National Association for Fruit Growers | NARF | Michurinsk | partner | [6 empty] | WG2 |  |  |  | 933187046 | validated | anto-milyaev@yandex.ru
P21 | People’s Khural of the Republic of Buryatia | PHRB | Ulan-Ude | partner | [6 empty] | WG3 |  |  |  | 933337687 | validated | kom.agrar@yandex.ru
P22 | JASSO TOUR Co LTD | JASSO TOUR | Ulan-Ude | partner | [6 empty] | WG3 |  |  |  | 933708033 | validated | info@jassotour.ru
P23 | Association of forestry and wood processing organizations of the Republic of Kazakhstan Zhasyl Orman | AFWPO RK Zhasyl Orman | Astana | partner | [6 empty] | WG4 |  |  |  | 932447615 | validated | oyl_zhasylorman@mail.ru
P24 | Republican Public Association 'Kazakhstan Farmers Union' | RPA KFU | Astana | partner | [6 empty] | WG4 |  |  |  | 932438109 | declared | ard_astana@mail.ru
P25 | Department of Agriculture of Kostanay Region Akimat | DAKRA | Kostanay | partner | [6 empty] | WG5 |  |  |  | 933409176 | sleeping | baybosynmurzin@gmail.com
P26 | Public Association "Association of Farmers of Kostanay Region" | AFKR | Kostanay | partner | [6 empty] | WG5 |  |  |  | 932711455 | declared | oo-afko@mail.ru, zhetesamantayev@yandex.ru
P27 | Department of Agriculture in Akmola Region | DAAR | Kokshetau | partner | [6 empty] | WG6 |  |  |  | 932602330 | declared | akm.shu.disp@mail.ru
P28 | German Agrarian Centre Ltd. | DAZ | Chaglinka | partner | x | [5 empty] | WG6 |  |  |  | 933017393 | validated | Alexander.Toews@daz-kasachstan.net
P29 | Landesanstalt für Entwicklung der Landwirtschaft (LEL) | LEL | Schw. Gmünd | partner | [9 empty] | x | 933329636 | validated | Juergen.Kaesser@lel.bwl.de
P30 | Ministry of Agriculture of Russian Federation | MCX | Moscow | partner | x | [9 empty] | 932816991 | validated | toropov.54@mail.ru
P31 | Stolypin Centre of Regional Development | SCRD | Moscow | associate partner | [10 empty] | 933006626 | declared | N.Sluchevsky@stocen.org, nsluchevsky@gmail.com
P32 | Russian Committee for the UNESCO Program on Man and the Biosphere | MAB | Moscow | associate partner | [10 empty] | 932409785 | declared | yudgeb@gmail.com, dgebuadze@sevin.ru
P33 | Corvinus University of Budapest | BCE | Budapest | associate partner | [10 empty] | 999857086 | validated | gyorgy.pataki@uni-corvinus.hu
P34 | Association for Promotion of Entrepreneurial Activity in Kostanay region | APEAKR | Astana | associate partner | [10 empty] | 932698457 | sleeping | apeakr@yandex.ru

## WP1
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 5 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | % | 36 project months from 15.10.2015 until 14.10.2018
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
[6 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
1 | Analysis on rural development and skills demand | Preparation | P3 CULS
1,1 | Local working groups established | event | 0 | 0 | 0 | 0 | 0 | 0%
action | establishment of the local working groups | 0 | P6-11, 17-28 | 1 | 4 | 4 | 2 | 100% | bar: Oct.15 1 to Oct.15 3
1,2 | Situation analyses on rural development and job demands | report | 0 | 0 | 0 | 0 | 0 | 0%
action | description of framework conditions in the regions | 0 | P6-11, P1, P3, P5 | 1 | 4 | 4 | 2 | 100%
action | Summary on job skills demand | 0 | P6-11 | 2 | 6 | 4 | 5 | 100%
action | collection and analysis of existing study programme examples | 0 | P6-11, P12-16 | 2 | 6 | 4 | 10 | 100%
action | Presentation of results on labour market and job deman analysis on the Kick-off meeting | 0 | P6-11 | 7 | 1 | 7 | 1 | 100%

## WP2
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 4 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
[6 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
2 | Establishment of new study programme and courses | Development | P6 Omsk
2.1 | Outline and study requirements defined | report | 0 | 0 | 0 | 0 | 0 | 0%
action | Clarification of professional studies requirements and elaboration of proposals for study programme outline | 0 | P6-11 | 2 | 4 | 2 | 6 | 100%
action | Clarification of possibility to open master programme with 90 ECTS in Russia and in Kazakhstan | 0 | P6 | 4 | 2 | 4 | 15 | 60%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
action | Proposals of partner HEIs on outline of study programme | 0 | P6-11 | 4 | 2 | 4 | 6 | 100%
2.2 | Study programme elaborated | methodology | 0 | 0 | 0 | 0 | 0 | 0%
action | Proposals for final outline and content of the master programme on the kick-Off Meeting | 0 | P5, P6-11 | 7 | 1 | 7 | 1 | 100%
action | Definition of common general structure and content of study programme on the Kick-Off Meeting | 0 | P6-11 | 7 | 1 | 7 | 1 | 100%
action | Elaboration of study structure and draft syllabi of professional master | 0 | P6-11 | 5 | 6 | 6 | 14 | 95%
action | optional use of new courses in further education faculties | 0 | P6-11 | 5 | 12 | 7 | 13 | 95%
2.3 | Courses and modules are developed | service/ product | 0 | 0 | 0 | 0 | 0 | 0%
action | collection and research of existing module materials | 0 | P5-11 | 5 | 16 | 5 | 16 | 90%
action | development of new modules contents and detailed description | 0 | P6-11 | 10 | 14 | 10 | 14 | 65%
2.4 | Study programmes accredited, courses implemented | service/ product | 0 | 0 | 0 | 0 | 0 | 0%
action | developed study programmes are approved and recognised | 0 | P6-11 | 12 | 13 | 18 | 10 | 10%
action | course implementation and module conduction | 0 | P6-11 | 23 | 14 | 0 | 0 | 0%
2,5 | Meetings | report | 0 | 0 | 0 | 0 | 0 | 0%
action | First coordination meeting in Omsk, P6 | 0 | P6-P8, P1 | 5 | 1 | 5 | 1 | 100%
action | First coordination meeting in Astana, P9 | 0 | P9-P11, P1 | 6 | 1 | 5 | 1 | 100%

## WP3
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 2 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | %
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
according workplan, LFM, proposal | [5 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
3 | Capacity building of partner universities | Development | P2 WULS
3,1 | Equipment and literature purchased, equipment installed | teaching material | 0 | 0 | 0 | 0 | 0 | 0%
action | specification of equipment items and purchase | 0 | P6-11 | 5 | 21 | 12 | 14 | 20%
action | literature lists and purchase | 0 | P6-11 | 5 | 30 | 16 | 20 | 10%
3,2 | staff training and study trips to programme countries conducted | training material | 0 | 0 | 0 | 0 | 0 | 0%
action | 1st study trip to P2,3 + didactic seminar P29 | 0 | P6-11 | 9 | 1 | 13 | 1 | 100%
action | 2nd study trip to P1,4 + didactic seminar P29 | 0 | P6-11 | 13 | 1 | 18 | 1 | 0%
3,3 | Input/ backstopping visits from partner countries | event | 0 | 0 | 0 | 0 | 0 | 0%
action | visit and input of HEI partners in partner countries HEIs | 0 | 0 | 10 | 21 | 14 | 15 | 15%

## WP4
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 2 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | % | 36 project months from 15.10.2015 until 14.10.2018
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
[6 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
4 | Practise orientation and stakeholder involvement | Development | P4 HfWU
4.1 | Practical training elements defined and developed | report | 0 | 0 | 0 | 0 | 0 | 0%
action | specification of practical skills to be developed during studies | 0 | P6-11 | 3 | 9 | 5 | 15 | 75%
action | development of practical trainings and teaching formats | 0 | P6-11 | 7 | 17 | 7 | 17 | 75%
4.2 | Stakeholder involvement institutionalised | service/ product | 0 | 0 | 0 | 0 | 0 | 0%
action | local working groups regular consultations (~2/ month) | 0 | P6-11 | 3 | 34 | 4 | 33 | 47%
action | implementation of internship schemes and/or project work with practise partners | 0 | P6-11 | 6 | 31 | 6 | 31 | 45%

## WP5
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 2 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | %
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
[6 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
5 | Sustainable agriculture and rural development platforms | Development | P5 RSAU
5.1 | Knowledge platform (+web) designed and accessible | service/ product | 0 | 0 | 0 | 0 | 0 | 0%
action | Elaboration of the ideals for knowledge platform | 0 | P5, P9 | 4 | 4 | 4 | 17 | 90%
action | concept development of the national network platforms | 0 | 0 | 3 | 12 | 5 | 15 | 95%
action | elaboration of the services (web contents, information, links) | 0 | 0 | 12 | 20 | 14 | 20 | 25%
action | sustainability and maintenance of network platform | 0 | 0 | 30 | 7 | 0 | 0 | 0%
5.2 | Network Conferences are conducted | event | 0 | 0 | 0 | 0 | 0 | 0%
action | 1st project conference during project start phase | 0 | all | 7 | 1 | 7 | 1 | 100%
action | 2nd project conference interim | 0 | all | 19 | 1 | 22 | 1 | 0%

## WP6
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 2 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | %
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
[6 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
6 | Study information and results dissemination | Dissemination | P9 KATU
6.1 | Project website, partner websites, links created and maintained | service/ product | 0 | 0 | 0 | 0 | 0 | 0%
action | project website preparation and launch EN & RU | 0 | 0 | 2 | 5 | 2 | 5 | 100%
action | project website maintenance and updates/ links with partner homepages | 0 | 0 | 5 | 32 | 5 | 32 | 45%
6,2 | Study programme and project results information | service/ product | 0 | 0 | 0 | 0 | 0 | 0%
action | elaboration of information material on study programmes | 0 | 0 | 12 | 13 | 18 | 7 | 10%
action | information events and dissemination of materials | 0 | 0 | 19 | 18 | 0 | 0 | 0%

## WP7
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 2 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | %
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
[6 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
7 | Quality control and monitoring | Quality Plan | P1/P5
7.1 | M&E tools for project progress elaborated and iplemented | report | P1 UHOH | 0 | 0 | 0 | 0 | 0%
action | defining roles and procedures for project monitoring | 0 | 0 | 1 | 6 | 4 | 6 | 100%
action | Monitoring and reporting procedures of project progress established and communicated to project partners | 0 | 0 | 4 | 6 | 4 | 6 | 100%
action | monitoring and reporting of project progress | 0 | 0 | 4 | 33 | 4 | 33 | 47%
7.2 | Quality control of study plans and modules | report | P5 RSAU | 0 | 0 | 0 | 0 | 0%
action | definition of quality criteria for the study programme | 0 | 0 | 6 | 17 | 6 | 17 | 80%
action | presentation of quality criteria for the study programme at Kick-off | 0 | 0 | 7 | 1 | 7 | 1 | 100%
action | assessment of developed study plans and module performance | 0 | 0 | 23 | 14 | 0 | 0 | 0%

## WP8
SARUD Workplan
[9 empty] | month highlighted | [7 empty] | 7 |  |  |  | planned |  |  |  | actual state |  |  |  |  | % done |  |  |  | delayed ongoing | [9 empty] | % delayed finished
|  |  |  | planned | planned | actual | actual | % | 36 project months from 15.10.2015 until 14.10.2018
| Activities and Deliverables | Deliverable Type | LEAD | start month | duration | start | duration | done | Oct.15 | [11 empty] | Oct 16 | [11 empty] | Oct 17 | [9 empty] | Oct. 18
according workplan, LFM, proposal | [5 empty] | updates/ realized situation |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
8 | Project is successfully managed | Management | P1 UHOH
8.1 | Project steering committee meetings conducted | report | 0 | 0 | 0 | 0 | 0 | 0%
0 | 1SCM November 2015, Hohenheim | 0 | 0 | 2 | 0.4 | 2 | 0.4 | 100% | bar: Oct.15 2
0 | 2SCM April 2016, Omsk (together with 1 project conference) | 0 | 0 | 7 | 1 | 7 | 1 | 100%
0 | 3SCM October 2016, Warsaw | 0 | 0 | 13 | 1 | 13 | 1 | 100%
0 | 4SCM July 2017, Astana (together with interim conference) | 0 | 0 | 19 | 1 | 22 | 1 | 0%
0 | 5SCM January 2018, ? | 0 | 0 | 28 | 1 | 0 | 0 | 0%
0 | 6SCM September 2018, Moscow (plus final conference) | 0 | 0 | 35 | 1 | 0 | 0 | 0%
8.2 | Day to day management installed and in place | methodology | 0 | 0 | 0 | 0 | 0 | 0%
0 | project management tools installed | 0 | 0 | 1 | 6 | 1 | 6 | 100% | bar: Oct.15 1 to Oct.15 3
0 | regular aministrative, reporting and communication tasks | 0 | 0 | 1 | 36 | 1 | 36 | 50% | bar: Oct.15 1 to Oct.15 3
8,3 | Coordination of agreement tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0%
0 | participation in EACEA project management seminar | 0 | 0 | 5 | 1 | 4 | 1 | 100%
0 | implementation and coordination of agreement tasks | 0 | 0 | 1 | 36 | 4 | 33 | 48%
0 | List of project partners with updated contact information send around, availale in intranet and regularly updated if needed | 0 | P1 | 4 | 1 | 4 | 1 | 100%
0 | Elaboration and signing of Partnership Agreement | 0 | P1, all partners | 4 | 4 | 6 | 9 | 100%